## CTX Upgrades
Restaurant | RDO/AD | CTX/Grill
205 Riverside Dr TN | Andrew Dashkovitz | CTX | 40000
214 Franklin TN | Andrew Dashkovitz | CTX
216 Hermitage TN | Andrew Dashkovitz | CTX
263 Lebanon TN | Andrew Dashkovitz | CTX
388 Springfield TN | Andrew Dashkovitz | CTX
230 Eastgate OH | Richard Clark | CTX | 72000 | 64000 | Starting point based on Ray/Ken's recommendation. Greater growth potential from base numbers with Steak addition and Marketing
248 Springdale OH | Richard Clark | CTX
253 Western Hills OH | Richard Clark | CTX
326 Milford OH | Richard Clark | CTX
340 Middletown OH | Richard Clark | CTX
359 Cold Spring KY | Richard Clark | CTX
383 Mansfield OH | Richard Clark | CTX
404 Canal Winchester OH | Richard Clark | CTX
414 Harrison OH | Richard Clark | CTX
208 Kingston Pike TN | Tammy Padgett | CTX | 96000
249 Cleveland TN | Tammy Padgett | CTX
261 Alcoa TN | Tammy Padgett | CTX
278 Centerville GA | Tammy Padgett | CTX
300 Morristown TN | Tammy Padgett | CTX
312 Stockbridge GA | Tammy Padgett | CTX
330 Austell GA | Tammy Padgett | CTX
346 Hiram GA | Tammy Padgett | CTX
361 East Town TN | Tammy Padgett | CTX
366 Turkey Creek TN | Tammy Padgett | CTX
370 Ft. Oglethorpe GA | Tammy Padgett | CTX
415 Aiken SC | Tammy Padgett | CTX
334 Dickson TN | Andrew Dashkovitz | CTX/Flat | *recommend full conversion to SYS, indiviual quote (~$10,000 or slightly less)
294 Reynoldsburg OH | Richard Clark | CTX/Flat | *recommend full conversion to SYS, indiviual quote
270 Gallatin TN | Andrew Dashkovitz | CTX/Grill
342 Manchester TN | Andrew Dashkovitz | CTX/Grill
302 Hopkinsville KY | Andrew Dashkovitz | CTX/Grill
301 Concord NC | Tammy Padgett | CTX/Grill
310 Hickory NC | Tammy Padgett | CTX/Grill
424 Summerville SC | Tammy Padgett | CTX/Grill
275 Canton GA | Tammy Padgett | CTX/Grill*** | *just needs a 52" Atosa lowboy to finish CTX/Grill conversation, ~$4,500
206 Bowling Green KY | Andrew Dashkovitz | Grill
215 Hurstbourne Ln KY | Andrew Dashkovitz | Grill
232 Cookeville TN | Andrew Dashkovitz | Grill
233 Paducah KY | Andrew Dashkovitz | Grill
257 Owensboro KY | Andrew Dashkovitz | Grill
258 Elizabethtown KY | Andrew Dashkovitz | Grill
285 Tupelo MS | Andrew Dashkovitz | Grill
345 Marion IL | Andrew Dashkovitz | Grill
377 Olive Branch MS | Andrew Dashkovitz | Grill
413 Danville KY | Andrew Dashkovitz | Grill
356 Bellevue TN | Andrew Dashkovitz | Grill
225 Florence KY | Richard Clark | Grill
349 Ft. Wayne IN | Richard Clark | Grill
406 Greenwood IN | Richard Clark | Grill
284 Bloomington IN | Rick Clark | Grill
335 Southport IN | Rick Clark | Grill
373 Barboursville WV | Tammy Padgett | Grill
317 Panama City FL | Tammy Padgett | Grill
322 Charleston SC | Tammy Padgett | Grill
336 Glen Allen VA | Tammy Padgett | Grill
352 Christiansburg VA | Tammy Padgett | Grill
384 Chester VA | Tammy Padgett | Grill
397 N. Charleston SC | Tammy Padgett | Grill

## CTX Rollout Phase 1
Equipment
Total
| Restaurant | Address | City | State | Zip | RDO/AD | Order Date | Install Week | Go Live | Installer | Frt Comp. | Pro Number | Ship Date | 48" Char ($2,000) | Char Pan Rail ($200) | 52" Base ($4,800) | Slicer ($1,850) | Cost | 199500
1 | 312 Stockbridge GA | 3511 Hwy 138 SE | STOCKBRIDGE | GA | 30281 | Tammy Padgett |  | 2025-05-26 | 2025-06-02 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 7000 | P4 W1
2 | 330 Austell GA | 4130 Austell Road | AUSTELL | GA | 30106 | Tammy Padgett |  | 2025-05-26 | 2025-06-02 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 28000 | P4 W2
3 | 346 Hiram GA | 4790 Jimmy Lee Smith Pkwy. | HIRAM | GA | 30141 | Tammy Padgett |  | 2025-05-26 | 2025-06-02 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
4 | 278 Centerville GA | 2990 Watson Blvd. | CENTERVILLE | GA | 31028 | Tammy Padgett |  | 2025-06-02 | 2025-06-09 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
5 | 370 Ft. Oglethorpe GA | 2542 Battlefield Parkway | FT. OGELTHORPE | GA | 30742 | Tammy Padgett |  | 2025-06-02 | 2025-06-09 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
6 | 345 Marion IL | 2808 W. DeYoung Street | MARION | IL | 62959 | Steve Eberhart |  | 2025-04-14 | n/a | [7 empty] | Berkel Slicer | 1850 | 27400 | P4 W3
7 | 335 Southport IN | 6930 S. Emerson Ave. | INDIANAPOLIS | IN | 46237 | Richard Clark |  | 2025-04-07 | n/a | [7 empty] | Berkel Slicer | 1850
8 | 359 Cold Spring KY | 100 Crossroads Blvd. | COLD SPRING | KY | 41076 | Richard Clark |  | 2025-04-28 | 2025-05-05 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
9 | 383 Mansfield OH | 1335 N. Lexington-Spring Mill Road | MANSFIELD | OH | 44906 | Richard Clark |  | 2025-03-24 | 2025-03-31 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
10 | 294 Reynoldsburg OH | 2272 Baltimore/Reynoldsburg Rd | REYNOLDSBURG | OH | 43068 | Richard Clark |  | 2025-03-31 | 2025-04-07 |  |  |  |  | Atosa Char 48" & Rail | Atosa Worktop ($2,980) | 3x Induction ($2,470) | Berkel Slicer | 9700
11 | 404 Canal Winchester OH | 6224 North Davis Hwy | CANAL WINCHESTER | OH | 43110 | Richard Clark |  | 2025-03-31 | 2025-04-07 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base | Berkel Slicer | 7000 | 35000 | P4 W4
12 | 230 Eastgate OH | 4531 EASTGATE BLVD | CINCINNATI | OH | 45245 | Richard Clark |  | 2025-04-21 | 2025-04-28 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
14 | 326 Milford OH | 1088 State Route 28 | MILFORD | OH | 45150 | Richard Clark |  | 2025-04-21 | 2025-04-28 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
15 | 253 Western Hills OH | 5075 Crookshank Road | CINCINNATI | OH | 45238 | Richard Clark |  | 2025-04-28 | 2025-05-05 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
16 | 248 Springdale OH | 11315 Princeton Pike | SPRINGDALE | OH | 45246 | Richard Clark |  | 2025-05-05 | 2025-05-12 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
17 | 340 Middletown OH | 3446 Village Drive | FRANKLIN | OH | 45005 | Richard Clark |  | 2025-05-05 | 2025-05-12 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 14000 | P5 W1
18 | 414 Harrison OH | 616 Ring Road | HARRISON | OH | 45030 | Richard Clark |  | 2025-05-05 | 2025-05-12 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
19 | 424 Summerville SC | 315 Azalea Square Blvd | SUMMERVILLE | SC | 29483 | Tammy Padgett |  | 2025-04-14 | n/a | [7 empty] | Berkel Slicer | 1850 | 8850 | P5 W2
20 | 415 Aiken SC | 168 South Aiken Lane, Suite 300 | AIKEN | SC | 29803 | Tammy Padgett |  | TBD | TBD |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
21 | 232 Cookeville TN | 1401 INTERSTATE DRIVE | COOKVILLE | TN | 38501 | Steve Eberhart |  | 2025-03-31 | n/a | [7 empty] | Berkel Slicer | 1850 | 10700 | P5 W3
22 | 270 Gallatin TN | 1009 Village Green Crossing | GALLATIN | TN | 37066 | Steve Eberhart |  | 2025-03-31 | n/a | [7 empty] | Berkel Slicer | 1850
23 | 205 Riverside Dr TN | 674 North Riverside Drive | CLARKSVILLE | TN | 37040 | Steve Eberhart |  | 2025-04-07 | 2025-04-14 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
24 | 214 Franklin TN | 1202 Murfreesboro Road | FRANKLIN | TN | 37064 | Steve Eberhart |  | 2025-04-07 | 2025-04-14 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base | Berkel Slicer | 8850 | 17700 | P5 W4
25 | 342 Manchester TN | 2367 Hillsboro Blvd. | MANCHESTER | TN | 37355 | Steve Eberhart |  | 2025-04-07 | n/a | [7 empty] | Berkel Slicer | 1850
26 | 216 Hermitage TN | 5500 OLD HICKORY BLVD | HERMITAGE | TN | 37076 | Steve Eberhart |  | 2025-04-14 | 2025-04-21 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
27 | 263 Lebanon TN | 902 Murfreesboro Road | LEBANON | TN | 37090 | Steve Eberhart |  | 2025-04-14 | 2025-04-21 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 15850 | P6 W1
28 | 356 Bellevue TN | 110 Coley Davis Court | NASHVILLE | TN | 37221 | Steve Eberhart |  | 2025-04-14 | n/a | [7 empty] | Berkel Slicer | 1850
29 | 208 Kingston Pike TN | 8077 Kingston Pike | KNOXVILLE | TN | 37919 | Tammy Padgett |  | 2025-05-12 | 2025-05-19 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
30 | 300 Morristown TN | 3412 W. Andrew Johnson Hwy. | MORRISTOWN | TN | 37814 | Tammy Padgett |  | 2025-05-12 | 2025-05-19 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 21000 | P6 W2
31 | 361 East Town TN | 3050 South Mall Road | KNOXVILLE | TN | 37917 | Tammy Padgett |  | 2025-05-12 | 2025-05-19 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
32 | 249 Cleveland TN | 148 Paul Huff Parkway, N.W. | CLEVELAND | TN | 37312 | Tammy Padgett |  | 2025-05-19 | 2025-05-26 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
33 | 261 Alcoa TN | 364 Fountain view Circle | ALCOA | TN | 37701 | Tammy Padgett |  | 2025-05-19 | 2025-05-26 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000 | 14000 | P6 W3
34 | 366 Turkey Creek TN | 11036 Parkside Drive | KNOXVILLE | TN | 37934 | Tammy Padgett |  | 2025-05-19 | 2025-05-26 |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
13 | 388 Springfield TN | 3535 Tom Austin Hwy. | SPRINGFIELD | TN | 37172 | Steve Eberhart |  | TBD | TBD |  |  |  |  | Atosa Char 48" | Custom Pan Rail | 52" Atosa Equipment Base |  | 7000
35 | 384 Chester VA | 12301 Bermuda Cross Roads Lane | CHESTER | VA | 23831 | Tammy Padgett |  | 2025-04-07 | n/a | [7 empty] | Berkel Slicer | 1850
[12 empty] | *** All Slicers in by 4/21 *** |  |  | TOTAL | 0 |  | 199500
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Line Spec
CTX plus Char Line Setup *All lines need to be in this configuration
Tender Cooler | Sham (if) | 52" Refrigerated Base w/ Char Grill | CTX |  | CTX Load
| Possible Re-work Needed: |  |  | Vendor
| **Might need to have ansul lines repositioned |  |  | Fire
| **Might need to have CTX electrical extended |  |  | Electrician
| **Might need to have gas line for Char repositioned |  |  | Equipment or Plumber

## Sheet1
205 O'Charley's | 674 North Riverside Drive | CLARKSVILLE | TN | 37040
208 O'Charley's | 8077 Kingston Pike | KNOXVILLE | TN | 37919
214 O'Charley's | 1202 Murfreesboro Road | FRANKLIN | TN | 37064
216 O'Charley's | 5500 OLD HICKORY BLVD | HERMITAGE | TN | 37076
230 O'Charley's | 4531 EASTGATE BLVD | CINCINNATI | OH | 45245
232 O'Charley's | 1401 INTERSTATE DRIVE | COOKVILLE | TN | 38501
248 O'Charley's | 11315 Princeton Pike | SPRINGDALE | OH | 45246
249 O'Charley's | 148 Paul Huff Parkway, N.W. | CLEVELAND | TN | 37312
253 O'Charley's | 5075 Crookshank Road | CINCINNATI | OH | 45238
261 O'Charley's | 364 Fountain view Circle | ALCOA | TN | 37701
263 O'Charley's | 902 Murfreesboro Road | LEBANON | TN | 37090
270 O'Charley's | 1009 Village Green Crossing | GALLATIN | TN | 37066
278 O'Charley's | 2990 Watson Blvd. | CENTERVILLE | GA | 31028
294 O'Charley's | 2272 Baltimore/Reynoldsburg Rd | REYNOLDSBURG | OH | 43068
300 O'Charley's | 3412 W. Andrew Johnson Hwy. | MORRISTOWN | TN | 37814
312 O'Charley's | 3511 Hwy 138 SE | STOCKBRIDGE | GA | 30281
326 O'Charley's | 1088 State Route 28 | MILFORD | OH | 45150
330 O'Charley's | 4130 Austell Road | AUSTELL | GA | 30106
335 O'Charley's | 6930 S. Emerson Ave. | INDIANAPOLIS | IN | 46237
340 O'Charley's | 3446 Village Drive | FRANKLIN | OH | 45005
342 O'Charley's | 2367 Hillsboro Blvd. | MANCHESTER | TN | 37355
345 O'Charley's | 2808 W. DeYoung Street | MARION | IL | 62959
346 O'Charley's | 4790 Jimmy Lee Smith Pkwy. | HIRAM | GA | 30141
356 O'Charley's | 110 Coley Davis Court | NASHVILLE | TN | 37221
359 O'Charley's | 100 Crossroads Blvd. | COLD SPRING | KY | 41076
361 O'Charley's | 3050 South Mall Road | KNOXVILLE | TN | 37917
366 O'Charley's | 11036 Parkside Drive | KNOXVILLE | TN | 37934
370 O'Charley's | 2542 Battlefield Parkway | FT. OGELTHORPE | GA | 30742
383 O'Charley's | 1335 N. Lexington-Spring Mill Road | MANSFIELD | OH | 44906
384 O'Charley's | 12301 Bermuda Cross Roads Lane | CHESTER | VA | 23831
388 O'Charley's | 3535 Tom Austin Hwy. | SPRINGFIELD | TN | 37172
404 O'Charley's | 6224 North Davis Hwy | CANAL WINCHESTER | OH | 43110
414 O'Charley's | 616 Ring Road | HARRISON | OH | 45030
415 O'Charley's | 168 South Aiken Lane, Suite 300 | AIKEN | SC | 29803
424 O'Charley's | 315 Azalea Square Blvd | SUMMERVILLE | SC | 29483